## Sheet1
Issue Type | Key | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due date
Task | SCRUM-31 | Implement back-end API to save a new task. | Aizaz Ahmed | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:17 | 2024-12-30 01:17
Story | SCRUM-30 | As a user, I want to edit an existing task’s details (title, description, due date), so I can update my task information. | Aizaz Ahmed | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:17 | 2024-12-30 01:17
Task | SCRUM-29 | Build front-end UI form for new task creation. | Muhammad Hashir | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:16 | 2024-12-30 01:21
Story | SCRUM-28 | As a user, I want to create a new task with a title, due date, and priority, so I can plan my tasks effectively. | Muhammad Hashir | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:16 | 2024-12-30 01:21
Task | SCRUM-27 | Integrate front-end and back-end and test. | Muhammad Abdullah Sarwar | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:16 | 2024-12-30 01:21
Story | SCRUM-26 | As a user, I want to edit an existing task’s details (title, description, due date), so I can update my task information. | Muhammad Abdullah Sarwar | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:16 | 2024-12-30 01:21
Task | SCRUM-25 | Implement back-end API to save a new task. | Muhammad Abdullah Sarwar | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:15 | 2024-12-30 01:21
Story | SCRUM-24 | As a user, I want to create a new task with a title, due date, and priority, so I can plan my tasks effectively. | Muhammad Abdullah Sarwar | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:15 | 2024-12-30 01:21
Task | SCRUM-23 | Integrate front-end and back-end and test. | Aizaz Ahmed | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:14 | 2024-12-30 01:14
Story | SCRUM-22 | As a user, I want to edit an existing task’s details (title, description, due date), so I can update my task information. | Aizaz Ahmed | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:14 | 2024-12-30 01:14
Task | SCRUM-21 | Build front-end UI form for new task creation. | Muhammad Hashir | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:14 | 2024-12-30 01:20
Story | SCRUM-20 | As a user, I want to create a new task with a title, due date, and priority, so I can plan my tasks effectively. | Muhammad Hashir | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:13 | 2024-12-30 01:20
Epic 1 | SCRUM-19 | Focus Task | Aizaz Ahmed | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:12 | 2024-12-30 01:13
Epic 1 | SCRUM-18 | Task Tracking & Progress | Aizaz Ahmed | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:09 | 2024-12-30 01:09
Epic 1 | SCRUM-17 | Task Creation & Editing | Aizaz Ahmed | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:09 | 2024-12-30 01:09
Task | SCRUM-16 | Implement back-end API to save a new task. | Aizaz Ahmed | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:06 | 2024-12-30 01:06
Story | SCRUM-15 | As a user, I want to edit an existing task’s details (title, description, due date), so I can update my task information. | Aizaz Ahmed | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:06 | 2024-12-30 01:06
Task | SCRUM-14 | Build front-end UI form for new task creation. | Muhammad Abdullah Sarwar | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:05 | 2024-12-30 01:20
Story | SCRUM-13 | As a user, I want to create a new task with a title, due date, and priority, so I can plan my tasks effectively. | Muhammad Abdullah Sarwar | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:04 | 2024-12-30 01:19
Epic 1 | SCRUM-12 | Project/Group Management | Aizaz Ahmed | Aizaz Ahmed | Medium | To Do |  | 2024-12-30 01:03 | 2024-12-30 01:03
NFR 1 | SCRUM-8 | App should be easy to navigate and use. | Aizaz Ahmed | Aizaz Ahmed | Medium | To Do |  | 2024-12-26 15:58 | 2024-12-26 15:58
Story | SCRUM-3 | DELETE EXISTING TASK | Muhammad Hashir | Aizaz Ahmed | Medium | To Do |  | 2024-12-26 15:10 | 2024-12-30 00:42
Story | SCRUM-2 | EDIT EXISTING TASK | Muhammad Abdullah Sarwar | Aizaz Ahmed | Medium | To Do |  | 2024-12-26 15:09 | 2024-12-30 00:42
Story | SCRUM-1 | CREATE NEW TASK | Aizaz Ahmed | Aizaz Ahmed | Medium | To Do |  | 2024-12-26 15:08 | 2024-12-30 00:41

## EC365_LOGGER (hidden)
$WORKSHEET_ID | 1 | "EC365_LOGGER"

## EC365_GLOBAL_SERIALIZATION (hidden)
$WORKSHEET_ID | 1 | "EC365_GLOBAL_SERIALIZATION"